## Sheet1
ID | Test Name | Tester of the code | Resources | Deadline | Status | Date completed | Comments
1 | Test main menu | Ivaylo Markov | Manually | 07.02.2022 | completed | 02.02.2022 | Main menu works perfectly
2 | Test open button in notebook | Ivaylo Markov | Manually | 07.02.2022 | completed | 03.02.2022 | Works well
3 | Test if entering an event in notebook works | Ivaylo Markov | Manually | 07.02.2022 | Partially working | 04.02.2022 | If you enter anything except a number the program returns: "Please enter a valid number:" infinitely
4 | Test escape button in notebook #1 | Ivaylo Markov | Manually | 08.02.2022 | Partially working | 04.02.2022 | If you anything except escape button the menu bugs the program and shows the notebook menu
5 | Test add event function in notebook | Ivaylo Markov | Manually | 08.02.2022 | completed | 07.02.2022 | No issues
6 | Test delete button in notebook #1 | Ivaylo Markov | Manually | 08.02.2022 | completed | 08.02.2022 | Delete function deletes all elements from the console and from the file
7 | Test collection in timeline | Ivaylo Markov | Manually | 09.02.2022 | completed | 09.02.2022 | Working without a problem
8 | Test add event function in timeline | Ivaylo Markov | Manually | 09.02.2022 | completed | 09.02.2022 | Add function goes to the adding options
9 | Test if adding an event in timeline works | Ivaylo Markov | Manually | 10.02.2022 | completed | 10.02.2022 | Adds properly
10 | Test back to menu button | Ivaylo Markov | Manually | 10.02.2022 | completed | 10.02.2022 | Works perfect
11 | Test search engine | Ivaylo Markov | Manually | 11.02.2022 | completed | 11.02.2022 | Searches events normally
12 | Test escape button in search engine | Ivaylo Markov | Manually | 12.02.2022 | completed | 12.02.2022 | Goes back how it is supposed to go
13 | Test delete button in notebook #2 | Ivaylo Markov | Manually | 13.02.2022 | completed | 13.02.2022 | Delete button now can delete every event in notebook